## Backlog
Backlog |  |  |  |  | Release Schedule
Tasks |  | Release | Estimate (Hours) | Iteration | Release | Hours Left | Hours per Iteration | Iterations Left
[5 empty] | Beta | 20 | 16 | 1.25
Web page layout |  |  |  |  | 1.0 | 46 | 16 | 2.875
| Base HTML Template | Beta | 4 | 1 | 2.0 | 8 | 16 | 0.5
| CSS | Beta | 4 | 1
Database
| Design user table | Beta | 8 | 1
| Define user ORM class | Beta | 4
| Define forum tables | 1.0 | 16
| Define forum ORM classes | 1.0 | 6
User profiles
| Login/logout subsystem | Beta | 16
| User profile page | 1.0 | 8
| Edit user profile | 1.0 | 16
| User stats page | 2.0 | 8

## Iteration #1
Iteration #1 |  | Start Date: | 2012-06-08 | Burndown
Tasks |  | Release | Estimate (Hours) | 1 | 2 | 3 | 4 | 5 | 6 | 7
Web page layout
| Base HTML Template | Beta | 4 | 3 | 2 | 2
| CSS | Beta | 4 | 4 | 4 | 1
Database
| Design user table | Beta | 8 | 8 | 8 | 8
Totals |  |  | 16 | 15 | 14 | 11
Ideal burndown |  |  |  | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 0